## Slide 1
Overall Concept:
System Diagram/ Concept Poster
Overall Project Deliverable | Progress
Minimal Changes Week to Week
Project is On Schedule
Project Name Team Members
Overview
As soon as this is available
Gantt Chart/Schedule

## Slide 2
Item | Description | Owner | Target Date | Status
1 |  |  |  | 
2 |  |  |  | 
3 |  |  |  | 
4 |  |  |  | 
5 |  |  |  | 
6 |  |  |  | 
Project Name Team Members
Previous Meeting Action Items:
Biweekly Action Items:
Significant Roadblocks/ Non-developing Items:
Feb |  |  |  |  |  |  |  |  |  | Feb |  |  |  | 
31 |  |  |  |  | 7 |  |  |  |  | 14 |  |  |  | 
Short Term Schedule:
Item | Description | Owner | Target Date | Status
1 |  |  |  | 
2 |  |  |  | 
3 |  |  |  | 
4 |  |  |  | 
5 |  |  |  | 
6 |  |  |  | 
Budget:
Total Proposed | Plan to Date | Used to Date | Used Vs Plan
$xxxx USD | $000USD | $000 USD | +/-$000 USD
Short-Term
As soon as this is available
Request for teaching staff:

## Slide 3: Add Detail sheets as necessary to clarify activity
Detail

## Slide 4
Example

## Slide 5
Overall Concept:
Overall Project Deliverable | Progress
Project Scope Decision | ⬛⬛⬛⬛⬛
Complete Electrical Block Diagram | ⬛⬛🟥⬜⬜
Complete 3D CAD for mechanical design | ⬛⬜⬜⬜⬜
Component selection/BOM selection | ⬜⬜⬜⬜⬜
Test Plan Creation | ⬜⬜⬜⬜⬜
Electrical Bench Test | ⬜⬜⬜⬜⬜
Mechanical Construction | ⬜⬜⬜⬜⬜
Testing | ⬜⬜⬜⬜⬜
Design Correction | ⬜⬜⬜⬜⬜
Project is On Schedule
Project Name Team Members
Overview
Gantt Chart/Schedule
Create remote-controlled Wheeled Robot with grasper capable of lifting 50 lbs

## Slide 6
Item | Description | Owner | Target Date | Status
1 | Decide microcontroller (Arduino vs Raspberry Pi) | Student B | 01-Feb | ⬜⬜⬜⬜⬜
2 | Finalize Motor Torque Calculation | Student A | 04-Feb | ⬛⬛⬛⬛⬜
3 | Create outer frame 3D CAD | Student C | 09-Feb | ⬛⬜⬜⬜⬜
4 | Create controller 3D CAD | Student A | 09-Feb | ⬜⬜⬜⬜⬜
5 | Robot Block Diagram Creation | Student B | 07-Feb | ⬜⬜⬜⬜⬜
6 | Controller Block Diagram | Student B | 12-Feb | ⬜⬜⬜⬜⬜
Project Name Team Members
Previous Meeting Action Items:
Biweekly Action Items:
Significant Roadblocks/ Non-developing Items:
Feb |  |  |  |  |  |  |  |  |  | Feb |  |  |  | 
31 |  |  |  |  | 7 |  |  |  |  | 14 |  |  |  | 
Short Term Schedule:
Item | Description | Owner | Target Date | Status
1 | Robot Manipulator Brainstorm | All | 02-Feb | ⬛⬛⬛⬛⬛
2 | Motor Torque Calculation | Student A | 27-Jan | ⬛⬛⬛⬛⬜
3 | Evaluate wireless communication protocol | Student B | 24-Jan | ⬛⬛⬛⬛⬛
4 |  |  |  | 
5 |  |  |  | 
6 |  |  |  | 
Budget:
Total Proposed | Plan to Date | Used to Date | Used Vs Plan
$1,250 USD | $000USD | $000 USD | +/-$000 USD
Short-Term
-Bluetooth-compatible Arduino shield is out of stock
-Team is struggling to gain access to 3D CAD tools
-Motor Torque Calculation is taking longer than expected
Project Plan
Initial Part Order
Significant Roadblocks/ Non-developing Items:
Request for teaching staff:
-Industry Mentor is being unresponsive. Help push mentors to attend weekly meetings

## Slide 7
2 Week Recap:
Option 1
Option 2
Option 3
Option 4
 | Option 1 | Option 2 | Option 3 | Option 4
Cost | S | - | + | ++
Number of Components | S | - | + | +
Complexity | S | - | S | +
Range of Motion | S | S | S | --
Durability | S | ++ | S | -
Grasping Ease | S | S | - | -
Total | 0 | -1 | +1 | 0
Robot Grasper direction has been decided
Detail