## Slide 1
Overall Concept:
Overall Project Deliverable | Progress
Basic Movement | Done
Image recognition | Done
New sensor implementation | In progress
Object following/Ball Striking | In progress
Co-op and Versus | Not started
Github with documentation | In progress
Summary and report | In progress
Project is On Schedule
Overview
Gantt Chart/Schedule
JetRacer Soccer Jarod Marshel, Casey Rittenhouse, Arjun Simha, Mason Kang, K Gupta, Julie Ham, Cooper Ritter
New Sensor

## Slide 2
Item | Description | Owner | Target Date | Status
1 | Object following | Everyone | Mar 8 | In progress
2 | Preliminary Design Review | Everyone | Mar 12 | In progress
3 | Implement new sensor onto car | Everyone | Mar 11 | In progress
4 |  |  |  | 
5 |  |  |  | 
JetRacer Soccer Jarod Marshel, Casey Rittenhouse, Arjun Simha, Mason Kang, K Gupta, Julie Ham, Cooper Ritter
Previous Meeting Action Items:
Significant Roadblocks/ Non-developing Items:
March |  |  |  |  |  |  |  |  |  | Feb |  |  |  | 
4 |  |  |  |  | 11 | 12 |  |  |  |  |  |  |  | 
Short Term Schedule:
Item | Description | Owner | Target Date | Status
1 | Build field for cars | Jarod | Feb 19 | Done
2 | Unity soccer simulation training | Mason | Jan 31 | Done
3 | Object following | Everyone | Mar 8 | In progress
4 | Implement new sensor onto car | Everyone | Mar 11 | In progress
5 | Preliminary Design Review | Everyone | Mar 12 | In progress
6 |  |  |  | 
7 |  |  |  | 
Budget:
Total Proposed | Plan to Date | Used to Date | Used Vs Plan
$3500 USD | $0 USD | $0 USD | +/-$0 USD
Short-Term
Request for teaching staff:
Have presentation ready
Get car to follow ball
Biweekly Action Items:

## Slide 3: Team Progress

## Slide 4: ROS (Casey and Cooper)
JetRacer Soccer Jarod Marshel, Casey Rittenhouse, Arjun Simha, Mason Kang, K Gupta, Julie Ham, Cooper Ritter
Previous Work:
Established structure to control Zed servo
Continued to tune movement
Began converting ROS structure to Noetic
Updated documentation to make ROS implementation more straightforward
Future Work:
Work on Zed integration once CV team is ready
Work on winter presentation and report

## Slide 5: LiDAR (Arjun and Jarod)
JetRacer Soccer Jarod Marshel, Casey Rittenhouse, Arjun Simha, Mason Kang, K Gupta, Julie Ham, Cooper Ritter
Previous Work:
Worked on putting together the winter quarter presentation documenting all of our progress and the future progress we will be working on in the spring quarter.
Worked on putting together the design report for the winter quarter.
Future Work:
Once ZED testing is done in winter quarter, we will work on putting together a docker container to combine all of the packages on one car to be put on the rest of the three cars.
Need to fix up the other three cars and their parts, charge the batteries and controllers.
Want to fully setup the full field in the ECE basement soon to see how it looks and test it with the cars and the soccer ball

## Slide 6: Computer Vision (K and Julie)
JetRacer Soccer Jarod Marshel, Casey Rittenhouse, Arjun Simha, Mason Kang, K Gupta, Julie Ham, Cooper Ritter
Previous Work:
Old camera does not work anymore – hardware issue?
  gst_mini_object_set_qdata: assertion 'object != null' failed
  Shift focus to ZED2
Upgraded to Python3.8 (needed for YOLOv8)
Trained weights for YOLOv8
Reinstalled ZED SDK
Future Work:
Run a YOLOv8 detection program
Work with ROS team to set up publisher and subscriber for steering servo and ball following

## Slide 7: Unity (Mason)
JetRacer Soccer Jarod Marshel, Casey Rittenhouse, Arjun Simha, Mason Kang, K Gupta, Julie Ham, Cooper Ritter
Previous Work:
Create a 3rd year repo for the JetRacer project.
Optimize the Unity simulation as much as possible.
Future Work:
Furthur document the GitHub page.
Gather details about the Unity training and use them to prepare for the winter presentation.

## Slide 8: Team Roles
Project Manager - Jarod
Point of Contact - Arjun
Budget Manager - Casey
ROS/Hardware (Layout, PCB, CAD, LiDAR):
  Cooper, Casey, Jarod, Arjun
Unity Team:
  Mason
CV/Image Recognition Team:
  K, Julie

## Slide 9: Previous Year's Work
Built and gained full range of motion of 4 JetRacers using software
Set up a simulation environment to virtually train the agents
Structured a reward system for the reinforcement learning model
Implemented object detection model that identifies a soccer ball, opponent, and goal
Implemented software to follow and strike a ball
Developed logic process for striking a ball into a goal
Simulation results with reward structure demonstrate that agents can be trained to efficiently compete in a 2v2 soccer match
Created a GitHub page documenting the hardware and software instructions to setup JetRacers, a summary of the work completed, and plans for future work

## Slide 10: Our Final Deliverables
Demonstrate basic motion of JetRacer: 01/2024
Demonstrate JetRacer Image Recognition for soccer play: 01/2024
Trade study of possible sensor additions: 02/2024
Preliminary Design Review: 02/2024
Showcase vehicle scoring soccer ball in the goal in real-world: 03/2024
Add additional agents in the real world: 04/2024
Final Data Review: 05/2024