## Gantt Chart
GANTT CHART
PROJECT TITLE |  | JetRacer Soccer League |  |  | COMPANY NAME | [6 empty] | Lockheed Martin
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
[5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10
[5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Background and Context | 2024-01-03 | 2024-01-19 | 100% | bar: WEEK 1 W to WEEK 3 F
1.1.1 | Project Objectives and Deliverables | 2024-01-08 | 2024-01-19 | 100% | bar: WEEK 2 M to WEEK 3 F
2 | Project Definition and Planning
2.1 | Budget | 2024-01-10 | 2024-01-20 | 100% | bar: WEEK 2 W to WEEK 3 F
2.2 | Scope and Goal Setting | 2024-01-10 | 2024-01-27 | 100% | bar: WEEK 2 W to WEEK 4 F
3 | PHASE 1
3.1 | Research JetRacer | 2024-01-10 | 2024-01-27 | 100% | bar: WEEK 2 W to WEEK 4 F
3.2 | Initial Hardware | 2024-01-15 | 2024-01-31 | 100% | bar: WEEK 3 M to WEEK 5 W
3.3 | Basic Motion | 2024-01-15 | 2024-01-31 | 100% | bar: WEEK 3 M to WEEK 5 W
3.4 | Image Recognition | 2024-01-15 | 2024-01-31 | 100% | bar: WEEK 3 M to WEEK 5 W
4 | PHASE 2
4.1 | Sensor Trade Study | 2024-02-01 | 2024-02-12 | 100% | bar: WEEK 5 R to WEEK 7 M
4.2 | Sensor Implementation | 2024-02-05 | 2024-02-19 | 100% | bar: WEEK 6 M to WEEK 10 T
4.3 | Ball Following | 2024-02-01 | 2024-03-07 | 100% | bar: WEEK 5 R to WEEK 10 F
4.4 | Preliminary Design Review | 2024-02-26 | 2024-03-15 | 100% | bar: WEEK 9 M to WEEK 10 F
4.5 | Soccer Play | 2024-02-26 | 2024-03-15 | 10% | bar: WEEK 9 M to WEEK 10 F
4.6
Phase 1
| Implementation on another car | 2024-03-26 | 2024-04-02 | bar: WEEK 1 M to WEEK 2 T
| Update Image Recognition | 2024-03-26 | 2024-04-08 | bar: WEEK 1 M to WEEK 3 M
| 1v1 Soccer Play | 2024-03-26 | bar: WEEK 1 M to WEEK 5 F
| 1v1 Unity Soccer Simulation | 2024-04-08 | 2024-04-22 | bar: WEEK 3 M to WEEK 5 M
| Upgrade to Jetson Orin Nano | 2024-04-15 | bar: WEEK 4 M to WEEK 5 F
Phase 2
| Update Image Recognition | 2024-04-22 | 2024-05-06 | bar: WEEK 5 M to WEEK 7 M
| Implementation on all cars | 2024-04-22 | 2024-05-15 | bar: WEEK 5 M to WEEK 8 W
| Revamp Hardware |  | 2024-05-15 | bar: WEEK 7 M to WEEK 8 W
| Poster |  | 2024-05-21 | bar: WEEK 7 M to WEEK 9 T
| Final Report |  | 2024-06-05 | bar: WEEK 8 M to WEEK 10 F